## Sheet1
No | Task | Time(Hr) | Actual Start Date | Actual End Date | start date | End Date | Status | Execise |  | ModusTool Box | https://www.infineon.com/cms/en/design-support/tools/sdk/modustoolbox-software/?gad_source=1&gclid=CjwKCAiAiP2tBhBXEiwACslfnv0h0hMfq15glbZGa4s6xAV5yMGUm88b4GerS5EhOSXqgMAqH_8vZxoCGCEQAvD_BwE&gclsrc=aw.ds
1 | Modus Toobox steup | [8 empty] | User Guide | https://www.infineon.com/dgdl/Infineon-ModusToolbox_3.1_Eclipse_IDE_User_Guide-UserManual-v01_00-EN.pdf?fileId=8ac78c8c88704c7a0188a18b5cc24e4c&redirId=188241
2 | Run example code in IDE. This includes 1. How to build project? 2. How to debug project? 3. How to flash project? 4. Basic idea about KIT-Prog 5. How to create project? 6. How to import existing project? | 2 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | Done |  |  | Getting Started Guide | https://github.com/infineon/training-modustoolbox-level1-getting-started
3 | Understand device configurator tool and library manager tool | 6 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-16 | Done
4 | Understand what is PDL and HAL library? | 4 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | Done
5 | GPIO integration using LED and Button | 8 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | Done | 1.Read button On first press turn on LED On Second press turn off LED 2. Complete above exercise using interrupt | 3) BTN1-RED LED and BTN2-GREEN LED 4)any two btn one press LED on and second press LED off
6 | UART In PSoC6 (Retarget_io + PDL API) | 14 | 2026-02-20 | 2026-02-23 | 2026-02-20 | 2026-02-23 | Done |  |  | 1. Implement command based application.Application contains 5 command and it give unique response in each command
7 | Timer In Psoc Edge E84 | 12 | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-02-24 | Done | 1. Blink LED using TIMER
8 | I2C In PSoC Edge E84 | 16 | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | Done | 1.Read & Write RTC data using I2C
9 | SPI In PSoC6 | [6 empty] | 1.Interface SPI based OLED |  | https://fastbitlab.com/spi-behind-scene-data-communication-principle/#:~:text=The%20master%20SPI%20peripheral%20has,and%20one%20in%20the%20slave.
10 | Understand the USB CDC interface | 8 | 2026-02-06 | 2026-02-27 | 2026-02-06 | 2026-02-27 | Done |  |  | https://www.riyas.org/2013/12/online-led-matrix-font-generator-with.html |  | font
11 | Understand the Vglite example | 32 | 2026-02-09 |  | 2026-02-09 |  |  | 1.Take hello world project 2. Add "Read & Write RTC data using I2C" code On that and print the value on uart 3. Add Display related code and displayed the i2c output data on display as well